## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Manal mubarak Alaolaqi |  | 2. Save to one team member's Google drive
Thanwa Faraj Alqahtani |  | 3. Share file with other team members
Reuof Yousef Alyousef |  | 4. Edit First Names on this tab
Mona Mohammed Turki |  | 5. Add your team name to the name of this document
Maryam Abdulrahman Aleyid |  | 6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
1 | TR-1 | Define Project Scope | As a project team member, I want to define the project scope so that system boundaries and objectives are clearly identified. |  | 1-high | Done
1 | TR-2 | Identify Stakeholders | As a project manager, I want to identify stakeholders so that system requirements reflect user needs. | Admin and Staff roles. | 1-high | Done
1 | TR-3 | Create Product Backlog | As a product owner, I want to create a detailed backlog so that development tasks are organized and prioritized. | Requirement documentation | 1-high | Done
1 | TR-4 | Set Up Development Environment | As a developer, I want to configure development tools so that the team can collaborate efficiently. | GitHub and IDE setup. | 1-high | Done
1 | TR-5 | Design Database Structure | As a system designer, I want to design the database schema so that system data is stored accurately. | ER diagram and relationships | 1-high | Done
1 | TR-6 | Secure Login | As an admin, I want to log into the system securely so that unauthorized users cannot access sensitive data. | Authentication and encryption. | 1-high | Done
1 | TR-7 | Role-Based Access Control | As an admin, I want role-based access control so that staff can only access permitted features. | Admin vs Staff permissions. | 1-high | Done
1 | TR-8 | Create Train Schedule | As an admin, I want to create train schedules so that trains can be organized properly. | Route, time, pricing. | 1-high | Done
1 | TR-9 | Update Train Schedule | As an admin, I want to update train schedules so that changes are reflected accurately. | Maintain history. | 1-high | Done
1 | TR-10 | Define Seat Capacity | As an admin, I want to define seat capacity so that booking limits are controlled. | Linked to reservations. | 1-high | Done
1 | TR-11 | Set Ticket Pricing | As an admin, I want to set ticket prices so that revenue can be managed properly. | Flexible pricing model. | 1-high | Done
1 | TR-12 | Register Passenger | As a staff member, I want to register passengers so that their information is stored in the system. | Store ID and contact details. | 1-high | Done
1 | TR-13 | Create Reservation | As a staff member, I want to create reservations so that passengers can book tickets. | Core booking feature. | 1-high | Done
1 | TR-14 | Validate Seat Availability | As a staff member, I want seat validation so that overbooking does not occur. | Automatic validation. | 1-high | Done
1 | TR-15 | Automatic Seat Update | As a system, I want to update seat capacity automatically so that availability remains accurate. | Triggered after booking/cancel. | 1-high | Done
1 | TR-16 | Cancel Reservation | As a staff member, I want to cancel reservations so that seats can be reallocated. | Restore seat count. | 1-high | Done
1 | TR-17 | Data Validation Rules | As a system, I want input validation so that incorrect data is prevented. | Applies to all forms. | 1-high | Done
2 | TR-18 | Search Train Schedules | As a staff member, I want to search schedules so that I can find trips quickly. | Filter by route/date. | 1-high | Done
2 | TR-19 | Backup and Recovery | As a system admin, I want backup and recovery mechanisms so that data can be restored after failures. |  | 1-high | Done
2 | TR-20 | Data Integrity Constraints | As a system, I want integrity constraints so that database relationships remain consistent. | Foreign key enforcement | 1-high | Done
3 | TR-21 | Session Timeout | As a system admin, I want session timeout so that unattended sessions are automatically closed. | Security feature. | 1-high | Done
3 | TR-22 | Password Policy Enforcement | As an admin, I want strong password policies so that weak passwords are rejected. | Complexity rules. | 1-high | Done
3 | TR-23 | Account Lockout . | As a system, I want account lockout after failed attempts so that brute-force attacks are prevented |  | 1-high | Done
3 | TR-24 | System Availability | As an organization, I want high system availability so that operations are not interrupted. | Reliability improvements. | 1-high | Done
3 | TR-25 | Data Encryption | As a system admin, I want sensitive data encrypted so that data privacy is protected. | Encrypt stored data. | 1-high | Done
3 | TR-26 | Disaster Recovery Plan | As an organization, I want a disaster recovery plan so that service can resume quickly after major failures. | Recovery procedures. | 1-high | Done
1 | TR-28 | Delete Train Schedule | As an Admin, I want to delete outdated schedules so that the system remains accurate. | Prevent deletion with active bookings. | 2-medium | Done
1 | TR-29 | Update Passenger Profile | As a staff member, I want to update passenger information so that records remain accurate. | Edit contact details. | 2-medium | Done
1 | TR-30 | View Passenger History | As a staff member, I want to view booking history so that I can track past reservations. | Linked to reservation records. | 2-medium | Done
1 | TR-31 | Generate Booking Confirmation | As a staff member, I want booking confirmation so that passengers receive proof of reservation. |  | 2-medium | Done
1 | TR-32 | Basic Dashboard Summary | As an admin, I want to view system summary statistics so that performance can be monitored. | Total bookings & revenue. | 2-medium | Done
1 | TR-33 | Monitor Occupancy Rate | As an admin, I want occupancy tracking so that train performance is evaluated. |  | 2-medium | Done
2 | TR-34 | Search Passenger Records | As a staff member, I want to search passengers so that I can locate records easily. | Search by ID/name. | 2-medium | Done
2 | TR-35 | Modify Reservation | As a staff member, I want to modify reservations so that passengers can change trips when needed. | Change date/train. | 2-medium | Done
2 | TR-36 | Reservation Status Tracking | As a staff member, I want to track reservation status so that booking lifecycle is visible. | Pending/Confirmed/Cancelled. | 2-medium | Done
2 | TR-37 | Weekly Booking Report | As an admin, I want weekly booking reports so that performance trends are analyzed. |  | 2-medium | Done
2 | TR-38 | Monthly Booking Report | As an admin, I want monthly booking reports so that long-term demand is evaluated. |  | 2-medium | Done
2 | TR-39 | Revenue Analysis Report | As an admin, I want revenue reports so that financial performance can be evaluated. |  | 2-medium | Done
2 | TR-40 | Train Utilization Analysis | As an admin, I want utilization reports so that underperforming schedules are identified. |  | 2-medium | Done
2 | TR-41 | Error Handling | As a passeenger, I want clear error messages so that issues can be resolved quickly. |  | 2-medium | Done
2 | TR-42 | Export Reports | As an admin, I want to export reports so that they can be shared easily. | PDF/Excel export. | 2-medium | Done
3 | TR-43 | Audit Logging | As a system admin, I want audit logs so that key actions can be tracked for accountability. | Log create/update/delete. | 2-medium | Done
3 | TR-44 | Backup Monitoring | As a system admin, I want backup monitoring so that failed backups are detected early. | Backup logs & alerts. | 2-medium | Done
3 | TR-45 | Performance Optimization | As an admin, I want fast system response so that daily operations are efficient. |  | 2-medium | Done
2 | TR-46 | Contact as | As a passenger, i want to access contact information so that I can reach out for support or inquiries |  | 2-medium | Done
3 | TR-47 | implement Privacy Policy | As a passenger, I want to read the privacy policy so that I know how my personal data is being handled |  | 3-low | Done
2 | TR- 48 | Create an FAQ section | As a passenger, I want to view frequently asked questions so that I can find answers to common issues quickly |  | 3-low | Done
2 | TR-49 | Daily Booking Report | As an admin, I want daily booking reports so that operations can be reviewed. |  | 3-low | Done
2 | TR-50 | About as | As a passenger, i want to view the " Aboud as " page so that i can understand the organization mission and services |  | 3-low | Done
2 | TR-51 | Passenger Registration | As a passenger, i want to create a new account so that I can use the system |  | 3-low | Done
2 | TR-52 | Passenger Login | As a passenger, i want to log into my account so i can accsess my booking |  | 3-low | Done
2 | TR-53 | passenger self booking | As a passenger, i want to book a train ticket so that i can travel on a selected date. |  | 3-low | Done
2 | TR-54 | passenger cansel reservation | As a passenger , i want to cancel my reservation so that i can modify my travel plant |  | 3-low | Done

## Sprint1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
TR-1 | Define system objectives, and deliverables. | 3 | 2 | Reuof Yousef Alyousef | Done | 2026-02-23 | Start Date: | 2026-02-22 | Manal mubarak Alaolaqi | 6 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-1 | Define system boundaries, | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-02-23
TR-2 | List Admin and Staff roles and document expectations. | 2 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-02-25 | Sprint Length | 14 | Thanwa Faraj Alqahtani | 32 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-3 | Collect Requirement | 3 | 2 | Mona Mohammed Turki | Done | 2026-02-27
TR-3 | Organize user stories | 3 | 2 | Mona Mohammed Turki | Done | 2026-02-27 | Hours Per Day: | 9.2857 | Reuof Yousef Alyousef | 29 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-3 | Prioritize features | 2 | 3 | Mona Mohammed Turki | Done | 2026-02-27
TR-4 | Create a project repository and configure version control. | 2 | 1 | Thanwa Faraj Alqahtani | Done | 2026-02-27 |  |  | Mona Mohammed Turki | 24 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-4 | Install IDE, frameworks, and dependencies. | 3 | 2 | Thanwa Faraj Alqahtani | Done | 2026-02-27 |  |  | Maryam Abdulrahman Aleyid | 21 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-4 | Test environment setup | 1 | 3 | Thanwa Faraj Alqahtani | Done | 2026-02-27
TR-5 | Model entities | 3 | 3 | Manal mubarak Alaolaqi | Done | 2026-02-28 |  |  | #REF! | 0 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-5 | Implement tables. | 2 | 3 | Manal mubarak Alaolaqi | Done | 2026-02-28 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-5 | Enforce relational integrity between tables. | 3 | 3 | Manal mubarak Alaolaqi | Done | 2026-02-28 |  |  | Total: | 112 | #VALUE! | 0% | #NAME? | 0 | 0 | #NAME? | #REF!
TR-6 | Create user interface for login screen. | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-01 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-6 | Implement login authentecation | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-03
TR-6 | Encrypt password | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-03
TR-6 | test login functinolity | 2 | 1 | Thanwa Faraj Alqahtani | Done | 2026-03-03
TR-6 | Validate credentials against database | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-6 | Secure password storage using hashing. | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-7 | Define rule and promotion | 3 | 3 | Mona Mohammed Turki | Done | 2026-02-28
TR-7 | implement access control loginc | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-01 | [6 empty] | #NAME?
TR-7 | Test role-based restriction | 3 | 2 | Mona Mohammed Turki | Done | 2026-03-01 | [7 empty] | 0 | 0 | 112 | #REF!
TR-8 | Allow administrators to add new train schedules. | 3 | 2 | Reuof Yousef Alyousef | Done | 2026-03-01 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-8 | Build interface for adding/editing trains. | 3 | 2 | Reuof Yousef Alyousef | Done | 2026-03-01 | [7 empty] | 0 | 0 | 112 | #REF!
TR-8 | test schedule creation workflow | 2 | 1 | Reuof Yousef Alyousef | Done | 2026-03-01 | [6 empty] | #NAME?
TR-9 | Enable editing of schedule details. | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-03 | [7 empty] | 0 | 0 | 112 | #REF!
TR-9 | Test update scenarios | 3 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-03-03 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-28 | implement delete schedule | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-03 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-28 | Prevent deletion of trains with active bookings. | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-04 | [7 empty] | 0 | 0 | 112 | #REF!
TR-28 | Test delete scenarios | 2 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-10 | Ensure seat capacity input is valid. | 2 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-11 | design ticket price interfice | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-11 | Store and update ticket pricing. | 3 | 3 | Mona Mohammed Turki | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-11 | test peicing rule | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-12 | Create UI for passenger form | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-12 | Save passenger data in database. | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-03
TR-12 | test registration workflow | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-29 | implement profile edit functionality | 3 | 3 | Manal mubaral Alaolaqi | Done | 2026-03-04
TR-29 | Test profile update | 3 | 2 | Manal mubaral Alaolaqi | Done | 2026-03-04
TR-29 | validate data integrity | 1 | 1 | Manal mubaral Alaolaqi | Done | 2026-03-04
TR-30 | Retrieve previous reservations for passenger. | 3 | 2 | Manal mubaral Alaolaqi | Done | 2026-03-03 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-13 | design reservation form | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-13 | Implement reservation logic | 2 | 1 | Reuof Yousef Alyousef | Done | 2026-03-02
TR-13 | connect reservation to passenger and schedule | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-03
TR-13 | test booking workflow | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-04
TR-13 | Process booking transactions. | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-14 | Verify seats before confirming booking. | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-15 | Reduce seat count after booking confirmation. | 3 | 1 | Manal mubaral Alaolaqi | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-16 | Cancel booking and restore seat count. | 3 | 1 | Reuof Yousef Alyousef | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-31 | Create a confirmation message for the passenger. | 2 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-03-02 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-32 | Display total bookings and revenue overview. | 4 | 3 | Mona Mohammed Turki | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-33 | Calculate booked seats vs total capacity. | 3 | 2 | Manal mubaral Alaolaqi | Done | 2026-03-04 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
TR-17 | Validate forms to prevent incorrect entries. | 3 | 1 | Reuof Yousef Alyousef | Done | 2026-03-03 | [6 empty] | #NAME? | 0 | 0 | #NAME? | #REF!
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M13-[Current Completed Work], "")

## Sprint2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
TR-18 | Enable users to search train schedules based on route and travel date. | 3 | 3 | Manal mubarak Alaolaqi | Done | 2026-03-22 | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2026-03-05 | 0 | 0 | 102 | 102
TR- 18 | Design and implement interface filters that allow users to refine train search results.. | 3 | 2 | Manal mubarak Alaolaqi | Done | 2026-03-22 | Start Date: | 2026-03-05 | Manal mubarak Alaolaqi | 21 | 21 | 100% | #NAME? | 0 | 0 | #NAME? | 96.6316
TR- 34 | Allow administrators to search passengers using passenger ID or passenger name. | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-23 | Sprint Length | 19 | Thanwa Faraj Alqahtani | 21 | 21 | 100% | #NAME? | 0 | 0 | #NAME? | 91.2632
TR-35 | Develop the system logic that allows updating or modifying existing reservations. | 4 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-23 | Hours Per Day: | 5.3684 | Reuof Yousef Alyousef | 20 | 20 | 100% | #NAME? | 0 | 0 | #NAME? | 85.8947
TR-36 | Track reservation status such as Pending, Confirmed, and Cancelled | 3 | 3 | Reuof Yousef Alyousef | Done | 2026-03-25 |  |  | Mona Mohammed Turki | 20 | 20 | 100% | #NAME? | 0 | 0 | #NAME? | 80.5263
TR-49 | Create a database query that aggregates reservation data on a daily basis. | 3 | 3 | Reuof Yousef Alyousef | Done | 2026-03-23 |  |  | Maryam Abdulrahman Aleyid | 20 | 20 | 100% | #NAME? | 0 | 0 | #NAME? | 75.1579
TR-49 | Create UI for viewing daily reports. | 3 | 3 | Mona Mohammed Turki | Done | 2026-03-19 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 69.7895
TR-37 | Calculate weekly booking totals. | 3 | 3 | Mona Mohammed Turki | Done | 2026-03-27 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 64.4211
TR-38 | Calculate monthly booking totals. | 3 | 3 | Mona Mohammed Turki | Done | 2026-03-27 |  |  | Total: | 102 | 102 | 100% | #NAME? | 0 | 0 | #NAME? | 59.0526
TR-39 | Compute revenue based on ticket sales. | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-28 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 53.6842
TR-39 | Display revenue analysis dashboard. | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-28 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 48.3158
TR-40 | Calculate train utilization metrics. | 3 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-03-28 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 42.9474
TR-19 | Set up scheduled automatic backups for the project database. | 4 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-26 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 37.5789
TR- 19 | Verify recovery process works correctly | 3 | 3 | Thanwa Faraj Alqahtani | Done | 2026-03-26 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 32.2105
TR-20 | Apply referential integrity constraints | 3 | 3 | Manal mubarak Alaolaqi | Done | 2026-03-23 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 26.8421
TR-41 | Develop structured error handling for runtime and validation errors. | 3 | 3 | Manal mubarak Alaolaqi | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 21.4737
TR-42 | Enable users to export system reports in PDF format. | 3 | 3 | Reuof Yousef Alyousef | Done | 2026-03-25 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 16.1053
TR-42 | Enable users to export system reports in Excel format. | 3 | 3 | Reuof Yousef Alyousef | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 10.7368
TR-46 | Design a contact us page where users can view contact details or send inquiries | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-29 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 5.3684
TR-46 | Add a form allowing users to send messages or inquiries to the system administrator | 3 | 3 | Mona Mohammed Turki | Done | 2026-03-30 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 4.9738e-14
TR-48 | design the FAQ page | 3 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-03-30 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-48 | Implement common user questions and answers related to booking and schedules | 2 | 2 | Maryam Abdulrahman Aleyid | Done | 2026-03-30 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-50 | design about as page | 2 | 2 | Manal mubarak Alaolaqi | Done | 2026-03-31 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-50 | Implement the about us page to present information a bout the system | 2 | 2 | Manal mubarak Alaolaqi | Done | 2026-03-31 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-51 | review registration form | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-20 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-51 | Implement input validation | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-20 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-51 | test registration functionality | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-03-20 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-52 | review login form | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-03-21 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-52 | Implement authentication logic | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-21 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-52 | add error handling for incorrect login | 2 | 2 | Mona Mohammed Turki | Done | 2026-03-21 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-52 | test login functionality | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-22 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-53 | implement booking functionality | 3 | 2 | Manal mubarak Alaolaqi | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-53 | validate selected train and seat | 2 | 2 | Manal mubarak Alaolaqi | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-53 | check seat availability | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-53 | update seat status | 1 | 1 | Thanwa Faraj Alqahtani | Done | 2026-03-24 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-53 | system testing | 2 | 2 | Thanwa Faraj Alqahtani | Done | 2026-04-08 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-54 | implement cancel reservation features | 3 | 3 | Maryam Abdulrahman Aleyid | Done | 2026-04-07 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-54 | restore seat availability | 2 | 2 | Reuof Yousef Alyousef | Done | 2026-04-07 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-54 | test cancellation process | 2 | 2 | Mona Mohammed Turki | Done | 2026-04-07 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
TR-21 | Set a time limit for inactive users. | 4 | 4 | Thanwa Faraj Alqahtani | Done |  | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2026-03-15 | 0 | 0 | 150 | 150
TR-21 | Program the system to log out users automatically after timeout. | 4 | 4 | Thanwa Faraj Alqahtani | Done |  | Start Date: | 2026-03-15 | Manal mubarak Alaolaqi | 30 | 30 | 100% | #NAME? | 0 | 0 | #NAME? | 144
TR-21 | Show an alert before the session expires. | 4 | 4 | Thanwa Faraj Alqahtani | Done |  | Sprint Length | 25 | Thanwa Faraj Alqahtani | 30 | 30 | 100% | #NAME? | 0 | 0 | #NAME? | 138
TR-22 | Set rules for strong passwords (Length, Numbers, Symbols). | 4 | 3 | Reuof Yousef Alyousef | Done |  | Hours Per Day: | 6 | Reuof Yousef Alyousef | 30 | 30 | 100% | #NAME? | 0 | 0 | #NAME? | 132
TR-22 | Add a message to guide users when creating a password. | 4 | 3 | Reuof Yousef Alyousef | Done |  |  |  | Mona Mohammed Turki | 30 | 30 | 100% | #NAME? | 0 | 0 | #NAME? | 126
TR-22 | Ensure the system rejects weak passwords during registration | 4 | 3 | Reuof Yousef Alyousef | Done |  |  |  | Maryam Abdulrahman Aleyid | 30 | 30 | 100% | #NAME? | 0 | 0 | #NAME? | 120
TR-23 | Create a counter to track failed login attempts. | 4 | 3 | Manal mubarak Alaolaqi | Done |  |  |  | #REF! | 0 | 0 | 0% | #NAME? | 0 | 0 | #NAME? | 114
TR-23 | Lock the account after 5 failed tries. | 4 | 4 | Manal mubarak Alaolaqi | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 108
TR-23 | Add a timer to unlock the account automatically later. | 4 | 3 | Manal mubarak Alaolaqi | Done |  |  |  | Total: | 150 | 150 | 100% | #NAME? | 0 | 0 | #NAME? | 102
TR-24 | Monitor the server performance for 24/7 uptime. | 6 | 6 | Manal mubarak Alaolaqi | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 96
TR-24 | Optimize the code to handle multiple users at once. | 6 | 6 | Manal mubarak Alaolaqi | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 90
TR-24 | Set up alerts to notify the team if the site goes down. | 6 | 6 | Manal mubarak Alaolaqi | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 84
TR-25 | Implement hashing for user passwords in the database. | 6 | 5 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 78
TR-25 | Secure sensitive personal data so it is not readable as plain text. | 6 | 5 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 72
TR-25 | Test the database to ensure all private information is encrypted. | 6 | 5 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 66
TR-26 | Write a plan to restore the site after a crash. | 4 | 2 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 60
TR-26 | Simulate a failure and test how quickly we can resume service. | 4 | 2 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 54
TR-26 | Create a recovery checklist for the technical team. | 4 | 3 | Mona Mohammed Turki | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 48
TR-43 | Create a log file to track system actions (Create/Update/Delete). | 6 | 4 | Thanwa Faraj Alqahtani | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 42
TR-43 | Record the username and the timestamp for each activity | 6 | 4 | Thanwa Faraj Alqahtani | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 36
TR-43 | Design a simple dashboard for the admin to review these logs. | 6 | 3 | Thanwa Faraj Alqahtani | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 30
TR-44 | Set up a system to track if daily backups are successful. | 6 | 4 | Reuof Yousef Alyousef | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 24
TR-44 | Create simple logs to show the status of the last backup. | 6 | 4 | Reuof Yousef Alyousef | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 18
TR-44 | Verify that the system can be restored from the backup file. | 6 | 4 | Reuof Yousef Alyousef | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 12
TR-45 | Review the code to improve page loading speed. | 6 | 4 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 6
TR-45 | Optimize database queries for faster search results. | 6 | 5 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-45 | Optimize database queries for faster search results. | 6 | 3 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-47 | Write a clear privacy policy for user data handling. | 4 | 2 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-47 | Create a dedicated page to display the policy to passengers. | 4 | 2 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
TR-47 | Add a link to the policy in the website footer or signup page. | 4 | 1 | Maryam Abdulrahman Aleyid | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), N10-[Current Completed Work], "")